## Sheet1
Task: | Delivery By: | Item: | Complexity: | Value: | Status:
Segmentation | 2013-12-06 | Bayesian Classifier | High | This is the machine learning method that this segmentation process will use. | Done
Segmentation | 2013-12-13 | Parallelize Code | Low | Decrease the amount of computing time that segmentation needs. | Done
Segmentation | 2013-12-20 | Reduce false positives by 90% | Med | Removing the "Blue" in the accuracy visualizations. | Done
Segmentation | Jan, 2014 | Begin technique patenting process | ---
Segmentation | 2014-01-14 | All large vessel segmentation done by machine | High | Substantially reduces human time requirement. All large vessels will be segmented with minimal noise, holes or discontinuity. | Done
Segmentation & Separation | 2014-02-17 | Color Correction | Med/High | Allow a larger variety of input images and compensates for minor defects and dissimilarities in lighting | In Progress
Segmentation | 2014-02-21 | Automatic Process Testing and Improvement | Med/High | Fine tuning parameters and minor differences in techniques is time consuming. To overcome this large time sink, an EC2 server will be rented and tests will be automated. | In Progress
Segmentation & Separation | 2014-03-11 | Autonomous Continuity Reassembly | High | Segmentation often produces splintered and discontinuous vessels. This will further reduce human time requirements by intellligently determining which vessels should be continuous. | In Progress
Separation | 2014-04-08 | Implement first pass at artery/vein separation | High | Distinguish arteries from veins
Analysis & Segmentation | 2014-05-04 | Implement Voronoi Cell 'ideal' vasculature | Med | Provides "Ideal" vasculature model, goes hand-in-hand with continuity reassembly, and will help in back-checking segmentation quality.
Segmentation | June-August 2014 | Autonomous Segmentation | High | Completed during or before Beta testing.